## EA Cost
2022 Lightning Complex Restoration Project (EA)
CONSULTANT
DATE
FIELDWORK COST ESTIMATE ON TAB 3 (Fieldwork) OF THIS SHEET
TASK | DESCRIPTION | PROJECTED COST | Notes/Comments
Task 1 | Data Collection (rolled up total) | #NAME?
Task 1.1 | Setup Tasks and Geodatabase Establishment | #NAME?
Task 1.2 | Biological Resource Assessments & Evaluation | #NAME?
Task 1.3 | Silviculture / Fire and Fuels | #NAME?
Task 1.4 | Hydrology, Soils & Riparian Reserves Assessment | #NAME?
Task 1.5 | Cultural Resources / Heritage Resources / Archaeological Assessment | #NAME?
Task 1.6 | Recreation Assessment | #NAME?
Task 1.7 | Transportation | #NAME?
Task 2 | Meeting Coordination, Attendance, and Participation | #NAME?
Task 3 | Project Record Management (administrative records) and Document Management (Pinyon/Box drive) | #NAME?
Task 4 | Environmental Assessment, Conduct NEPA Scoping & Facilitate Decision Process | #NAME?
Task 4.1 | Public Engagement | #NAME?
Task 4.2 | Environmental Analysis | #NAME?
Task 4.3 | Formal Comment Period | #NAME?
Task 4.4 | Final NEPA Documents, Findings/Decisions & Objection Resolution | #NAME?
PROJECTED TOTAL

## CE Cost
Route 1 & 6 Timber Stand and Wildlife Habitat Improvements (CE)
CONSULTANT
DATE
FIELDWORK COST ESTIMATE ON TAB 3 (Fieldwork) OF THIS SHEET
TASK | DESCRIPTION | PROJECTED COST | Notes/Comments
Task 1 | Data Collection (rolled up total) | #NAME?
Task 1.1 | Setup Tasks and Geodatabase Establishment | #NAME?
Task 1.2 | Biological Resource Assessments & Evaluation | #NAME?
Task 1.3 | Silviculture / Fire and Fuels | #NAME?
Task 1.4 | Hydrology, Soils & Riparian Reserves Assessment | #NAME?
Task 1.5 | Cultural Resources / Heritage Resources / Archaeological Assessment | #NAME?
Task 1.6 | Recreation Assessment | #NAME?
Task 1.7 | Transportation | #NAME?
Task 2 | Meeting Coordination, Attendance, and Participation | #NAME?
Task 3 | Project Record Management (administrative records) and Document Management (Pinyon/Box drive) | #NAME?
Task 4 | Environmental Assessment, Conduct NEPA Scoping & Facilitate Decision Process | #NAME?
Task 4.1 | Public Engagement | #NAME?
Task 4.2 | Environmental Analysis | #NAME?
Task 4.3 | Formal Comment Period Task Not Required for CE
Task 4.4 | Final NEPA Documents, Findings/Decisions & Objection Resolution | #NAME?
PROJECTED TOTAL

## Fieldwork
2022 Lightning Complex Restoration Project (EA) & Route 1 & 6 Timber Stand and Wildlife Habitat Improvements (CE)
CONSULTANT
DATE
OPTION | Task | RESOURCE | Reconnisence Level Surveys | Field Survey | Consultant Costs | Subconsultant Costs | Total Option Cost | Cost per Unit (Field Days, Sites, or Acres)
Option A | 1.2 | Biological Resources Assessment & Evaluation - Invasive Plant Surveys | NA | EA: 373 Acres | $ | $ | $ | $
|  |  |  | CE: 303 Acres | $ | $ | $ | $
Option A Assumptions: | [6 empty] | $ | TOTAL
Option B | 1.3 | Silviculture / Fires and Fuels - Reconnaissance Surveys | EA: 10-15 Field Days | NA | $ | $ | $ | $
|  |  | CE: 3-5 Field days |  | $ | $ | $ | $
Option B Assumptions: | [6 empty] | $ | TOTAL
Option C.1 | 1.4 | Hydrology, Soils & Riparian Reserves Assessment - Riparian Reserve Flagging | NA | EA: 2,666 Acres | $ | $ | $ | $
|  |  |  | EA: 926 Acres | $ | $ | $ | $
Option C.1 Assumptions: | [6 empty] | $ | TOTAL
Option C.2 | 1.4 | Hydrology/Soils Assessment - Soils/Geology Surveys | NA | EA: 5-10 Field Days | $ | $ | $ | $
|  |  |  | CE: 2-3 Field Days | $ | $ | $ | $
Option C.2 Assumptions: | [6 empty] | $ | TOTAL
Option D | 1.5 | Archaeological Assessment - Section 106 and/or Reconnaissance Surveys | NA | EA: 6,457 Acres | $ | $ | $ | $
|  |  |  | CE: 2,626 Acres | $ | $ | $ | $
Option D Assumptions: | [6 empty] | $ | TOTAL